## Instructions
Seattle SCORE®
Starting a New Business
Instructions for Use:
Enter your Business Start Date (MM/DD/YY):
When you enter the date, the entries will be filled on the following worksheets.
Make any corrections to the duration of any of the tasks as you see fit.
After entering the starting date, select the "Tasks" tab below.
Quick Start Instructions:
On the "Tasks" worksheet, several fields may be changed to better suit your specific business.
These are:
Duration: | You may change the duration of any task by entering a new value in the field following
the task name. This number, which must be 1 or greater, sets the length of time in work
days for that task to be accomplished. As you change the values, the start and finish
dates for subsequent tasks will be adjusted.
Start Date: | The calculated Start Date for any task can be overridden. Enter the desired start date
in a MM/DD/YY format. If you wish to restore the calculated start date, just copy the
formula from another start date field to the one you changed by using the menu
"Edit/Copy" and "Edit/Paste" features.
Predecessor: | You may link the start date for a specific task to follow the completion of another
task by setting the value in the predecessor field. Set this value to the line number of the
task you want to follow. It must be less than the line number of the current task or an error
will occur.
The Task Names and Resource Names can be changed to better reflect your business, however this
version will not allow you to delete or add task lines. The Finish Date field is a calculated value and
may not be changed. More detailed information my be found in the instructions.
Copyright 2005 by Seattle Chapter #55, Service Corps of Retired Executives (SCORE)
All rights reserved.

## Tasks
Seattle SCORE®
Starting a New Business
PHASE 1, RESEARCH FOR YOUR PLANNED STARTUP | Duration | Start Date |  |  | Finish Date |  | Predecessor | Resource Name
Make Contact with a SCORE Counselor | 1 | Sun | 2007-08-26 10:42 | 3 | Tues | 2007-08-28 10:42 |  | Client & SCORE Counselor
Familiarize Yourself with SCORE Resources | 2 | Wed | 2007-08-29 10:42 | 2 | Thur | 2007-08-30 10:42 | 5 | Client
Consider Your Options for Starting New New Business | 17 | Wed | 2007-08-29 10:42 | 23 | Thur | 2007-09-20 10:42 | 5 | (1) Buy a Franchise, (2) Buy a Business, (3) Start Your Own Business
Attend the SCORE Starting a New Business Workshop | 17 | Wed | 2007-08-29 10:42 | 23 | Thur | 2007-09-20 10:42 | 5 | SCORE New Business Workshop Offered Monthly
Conduct Market Research for Your New Business Startup | 17 | Wed | 2007-08-29 10:42 | 23 | Thur | 2007-09-20 10:42 | 5 | SCORE Business Center & Public Library
Contact Product Suppliers, Obtain Wholesale Product Catalogs | 17 | Wed | 2007-08-29 10:42 | 23 | Thur | 2007-09-20 10:42 | 5 | Client
Obtain a Dept. of Construction & Land Use Building Permit Application | 17 | Wed | 2007-08-29 10:42 | 23 | Thur | 2007-09-20 10:42 | 5 | Client if Construction is Required
Study the Real Estate Market for Suitable Business Locations | 17 | Wed | 2007-08-29 10:42 | 23 | Thur | 2007-09-20 10:42 | 5 | Client & Realtor
Determine the Lease and Building Costs for Desirable Locations | 17 | Wed | 2007-08-29 10:42 | 23 | Thur | 2007-09-20 10:42 | 5 | Client & Realtor
Visit a Business Similar to the One You are Planning to Start | 17 | Wed | 2007-08-29 10:42 | 23 | Thur | 2007-09-20 10:42 | 5 | Client Research
Study Their Product Pricing, Product Quality, Hours of Operation | 17 | Wed | 2007-08-29 10:42 | 23 | Thur | 2007-09-20 10:42 | 5 | Client Research
Study Their Location, Arrangement and Facilities customer Sources | 17 | Wed | 2007-08-29 10:42 | 23 | Thur | 2007-09-20 10:42 | 5 | Client Research
Study Their Customer Service Marketing & Advertising, and Their Website | 17 | Wed | 2007-08-29 10:42 | 23 | Thur | 2007-09-20 10:42 | 5 | Client
Obtain Ideas for Your Planned Business Startup | 17 | Wed | 2007-08-29 10:42 | 23 | Thur | 2007-09-20 10:42 | 5 | Client Research
Develop a Preliminary Space Layout for Your Business | 17 | Wed | 2007-08-29 10:42 | 23 | Thur | 2007-09-20 10:42 | 5 | Client
Make Your Capitalization and Startup Expense Estimate | 17 | Wed | 2007-08-29 10:42 | 23 | Thur | 2007-09-20 10:42 | 5 | Use the CD Expense Spreadsheet
If Financing is Needed, Attend an SBA Loan Briefing | 17 | Wed | 2007-08-29 10:42 | 23 | Thur | 2007-09-20 10:42 | 5 | SBA Loan Briefing Session are Held Twice Monthly
If Financing is Needed, Contact Banks & Alternative Lenders | 17 | Wed | 2007-08-29 10:42 | 23 | Thur | 2007-09-20 10:42 | 5 | Determine the Lender's Debt Repayment and Collateral Requirements
If Financing is Needed, Attend a SCORE Money/Finance Workshop | 24 | Wed | 2007-08-29 10:42 | 32 | Mon | 2007-10-01 10:42 | 5 | See SCORE Workshop Schedule for Next Workshop Date
Develop a Preliminary First Year Sales Revenue Projection | 17 | Wed | 2007-08-29 10:42 | 23 | Thur | 2007-09-20 10:42 | 5 | Client
If Financing is Needed, Obtain a Copy of SBA Loan Fact Sheet | 1 | Fri | 2007-09-21 10:42 | 1 | Fri | 2007-09-21 10:42 | 22 | Defines SBA's Loan,Credit,and Repayment Requirements
Will You Have the Money & Financing for Your New Business? | 3 | Mon | 2007-09-24 10:42 | 3 | Wed | 2007-09-26 10:42 | 25 | Do Not Continue Until You Know That Financing Will be Available
Make Your Startup Decision - Is it a Go? | 2 | Thur | 2007-09-27 10:42 | 2 | Fri | 2007-09-28 10:42 | 26 | Client
Work with Your SCORE Counselor on Your Decision | 1 | Mon | 2007-10-01 10:42 | 1 | Mon | 2007-10-01 10:42 | 27 | Client & SCORE Business Counselor
END OF PHASE 1, RESEARCH FOR YOUR PLANNED STARTUP | 26 | Sun | 2007-08-26 10:42 | 36 | Mon | 2007-10-01 10:42 |  | YOU SHOULD HAVE MADE A STARTUP DECISION
PHASE 2, BUILDING THE BUSINESS PLAN | Duration | Start Date |  |  | Finish Date |  | Predecessor | Resource Name
Ensure Your Computer has Capacity for the Business Plan Templates | 1 | Tues | 2007-10-02 10:42 | 1 | Tues | 2007-10-02 10:42 | 29 | Upgrade or Purchase a New Computer with Capacity for the Templates
Make a Schedule for the Work Involved in Building a Business Plan | 2 | Tues | 2007-10-02 10:42 | 2 | Wed | 2007-10-03 10:42 | 29 | Work with Your SCORE Counselor for Assistance
Attend the SCORE Building a Business Plan Workshop | 30 | Thur | 2007-10-04 10:42 | 42 | Wed | 2007-11-14 10:42 | 33 | SCORE Business Plan Workshop Offered Monthly
Start the Business Plan with the Marketing Plan | 5 | Thur | 2007-10-04 10:42 | 7 | Wed | 2007-10-10 10:42 | 33 | Client
Update Your Preliminary First Year Revenue Sales Projection | 5 | Thur | 2007-10-04 10:42 | 7 | Wed | 2007-10-10 10:42 | 33 | Client
SCORE Marketing Counselor Review of Your Marketing Plan | 14 | Thur | 2007-10-11 10:42 | 20 | Tues | 2007-10-30 10:42 | 36 | Schedule this Review Well in Advance
Select a Business Organization for Your Startup | 3 | Thur | 2007-10-04 10:42 | 3 | Mon | 2007-10-08 10:42 | 33 | Some Considerations are: Investors,Legal Risk,& Taxes
Prepare a Business Organization for Your Legal Entity | 7 | Tues | 2007-10-09 10:42 | 9 | Wed | 2007-10-17 10:42 | 38 | Client Options: Sole Prop.,Partnership,LP,LLC,& Corporation
Review of Your Business Entity and Organization with Investors | 1 | Thur | 2007-10-18 10:42 | 1 | Thur | 2007-10-18 10:42 | 39 | Client & Investors
Attend Product Trade Shows for Business Ideas | 60 | Tues | 2007-10-02 10:42 | 84 | Mon | 2007-12-24 10:42 | 29 | Client
Select a Company Name | 1 | Thur | 2007-10-18 10:42 | 1 | Thur | 2007-10-18 10:42 | 39 | Client can Access WA State Trade Name Data Base for Availability
Legal Review of Your Business Organization | 1 | Fri | 2007-10-19 10:42 | 1 | Fri | 2007-10-19 10:42 | 42 | Attorney
Update Your Preliminary Space Arrangement Concept & Menus | 4 | Mon | 2007-10-22 10:42 | 4 | Thur | 2007-10-25 10:42 | 43 | Client
Select the Top Location Choices and Determine their Costs | 10 | Fri | 2007-10-26 10:42 | 14 | Thur | 2007-11-08 10:42 | 44 | Client & Real Estate Agent
Determine Employee Requirements and Costs | 5 | Fri | 2007-11-09 10:42 | 7 | Thur | 2007-11-15 10:42 | 45 | Client
Update Your Capitalization and Startup Expense Estimate | 4 | Fri | 2007-11-16 10:42 | 6 | Wed | 2007-11-21 10:42 | 46 | Use the CD Expense Spreadsheet
Make optimistic & Pessimistic Projections for: | 15 | Thur | 2007-11-22 10:42 | 21 | Wed | 2007-12-12 10:42 | 47 | Client
(1) Sales Forecasts | 15 | Thur | 2007-11-22 10:42 | 21 | Wed | 2007-12-12 10:42 | 47 | Client
(2) First Year & Four Year Cash Flow Projections | 15 | Thur | 2007-11-22 10:42 | 21 | Wed | 2007-12-12 10:42 | 47 | Client
(3) First Year & Four Year Profit and Loss Projections | 15 | Thur | 2007-11-22 10:42 | 21 | Wed | 2007-12-12 10:42 | 47 | Client
(4) Opening Day & Projected Balance Sheet Projections | 15 | Thur | 2007-11-22 10:42 | 21 | Wed | 2007-12-12 10:42 | 47 | Client
(5) Working Capital Required for Pessimistic Projections | 15 | Thur | 2007-11-22 10:42 | 21 | Wed | 2007-12-12 10:42 | 47 | Client
(6)) Breakeven Analysis & Loan Amortization | 15 | Thur | 2007-11-22 10:42 | 21 | Wed | 2007-12-12 10:42 | 47 | Client
(7) Financial History & Personal Financial Statement | 15 | Thur | 2007-11-22 10:42 | 21 | Wed | 2007-12-12 10:42 | 47 | Client
Develop Your Business Operations Plan | 3 | Fri | 2007-11-16 10:42 | 5 | Tues | 2007-11-20 10:42 | 46 | Client
Complete Your Financial Plan | 5 | Wed | 2007-11-21 10:42 | 7 | Tues | 2007-11-27 10:42 | 56 | Client
Compare Your Financial Projections With Industry Standards | 1 | Wed | 2007-11-28 10:42 | 1 | Wed | 2007-11-28 10:42 | 57 | Robert Morse & Other Comparison Data Available in SCORE SBC
SCORE Financial Counselor Review of Your Financial Plan | 7 | Thur | 2007-11-29 10:42 | 9 | Fri | 2007-12-07 10:42 | 58 | SCORE Counselor
Finalize the Complete Business Plan | 5 | Mon | 2007-12-10 10:42 | 7 | Fri | 2007-12-14 10:42 | 59 | Client
SCORE Counselor to Review Entire Completed Business Plan | 5 | Mon | 2007-12-17 10:42 | 7 | Fri | 2007-12-21 10:42 | 60 | Provides Comments& Recommendations on Your Business Plan
Actively Seek the Financing Needed | 23 | Thur | 2007-11-22 10:42 | 31 | Mon | 2007-12-24 10:42 | 47 | Banks,Alternative Lenders,Private Investors,Friends & Family
END OF PHASE 2, BUILDING THE BUSINESS PLAN | 60 | Tues | 2007-10-02 10:42 |  | Mon | 2007-12-24 10:42 |  | YOUR BUSINESS PLAN SHOULD BE COMPLETE and BANK READY
PHASE 3, FINANCING YOUR BUSINESS STARTUP | Duration | Start Date |  |  | Finish Date |  | Predecessor | Resource Name
OMIT PHASE 3 IF OUTSIDE FINANCING IN NOT NEEDED | [7 empty] | Client
Attend SBA Semi Monthly Loan Briefing for Any Loan Updates | 21 | Tues | 2007-12-25 10:42 | 29 | Tues | 2008-01-22 10:42 | 63 | SBA Loan Briefings Held Twice Monthly
Do You Have the Necessary Funding for Your Startup? | 21 | Tues | 2007-12-25 10:42 | 29 | Tues | 2008-01-22 10:42 | 63 | Client
SCORE Counselor with Banking Experience Review of Loan Package | 21 | Tues | 2007-12-25 10:42 | 29 | Tues | 2008-01-22 10:42 | 63 | Loan Package Review Prior to Submission to Lender
Obtain Your Financing | 21 | Tues | 2007-12-25 10:42 | 29 | Tues | 2008-01-22 10:42 | 63 | Client & Lender
Funding to Support Your Startup is Needed to Proceed Now | 21 | Tues | 2007-12-25 10:42 | 29 | Tues | 2008-01-22 10:42 | 63 | Stop Unless Financing is in Hand
END OF PHASE 3, FINANCING YOUR BUSINESS STARTUP | 21 | Tues | 2007-12-25 10:42 |  | Tues | 2008-01-22 10:42 |  | YOU SHOULD HAVE YOUR FINANCING IN HAND HERE
PHASE 4, OBTAIN PERMITS AND LICENSES | Duration | Start Date |  |  | Finish Date |  | Predecessor | Resource Name
Open a Business Checking Account | 6 | Wed | 2008-01-23 10:42 | 8 | Wed | 2008-01-30 10:42 | 72 | Client
Collect All License Documents, Read & Understand Them | 6 | Wed | 2008-01-23 10:42 | 8 | Wed | 2008-01-30 10:42 | 72 | Client
Obtain Washington Business License | 6 | Wed | 2008-01-23 10:42 | 8 | Wed | 2008-01-30 10:42 | 72 | Client
Obtain City or County Business License (If required} | 6 | Wed | 2008-01-23 10:42 | 8 | Wed | 2008-01-30 10:42 | 72 | Also any Specialty Permits (if required)
END PHASE 4, PERMITS AND LICENSE APPLICATIONS | 6 | Wed | 2008-01-23 10:42 |  | Wed | 2008-01-30 10:42 |  | YOU SHOULD UNDERSTAND THE PERMIT PROCESS & IT'S RISKS
PHASE 5, LEASE, SPACE DESIGN, & EQUIPMENT SELECTION | Duration | Start Date |  |  | Finish Date |  | Predecessor | Resource Name
Make Your Lease Decision Choice Based on Location & Cost | 3 | Thur | 2008-01-31 10:42 | 3 | Mon | 2008-02-04 10:42 | 79 | Client
Recommend Lease Review by SCORE Counselor | 1 | Tues | 2008-02-05 10:42 | 1 | Tues | 2008-02-05 10:42 | 82 | Client and SCORE Counselor
Prepare Letter of Intent to Lease | 1 | Wed | 2008-02-06 10:42 | 1 | Wed | 2008-02-06 10:42 | 83 | Client
Final Lease Negotiation With Leaser | 5 | Thur | 2008-02-07 10:42 | 7 | Wed | 2008-02-13 10:42 | 84 | Client & Leaser
Legal Review of Lease Before Signing | 1 | Thur | 2008-02-14 10:42 | 1 | Thur | 2008-02-14 10:42 | 85 | Client and Attorney
Order Business Cards and Print on 2 Sides | 3 | Fri | 2008-02-15 10:42 | 5 | Tues | 2008-02-19 10:42 | 86 | Client
Update Your Facility Design Concept ( Facility You Want Built) | 3 | Fri | 2008-02-15 10:42 | 5 | Tues | 2008-02-19 10:42 | 86 | Client
Contract with an Experienced Architect/Designer | 7 | Wed | 2008-02-20 10:42 | 9 | Thur | 2008-02-28 10:42 | 88 | Plans are Required for a Building Permit Application
Work With the Architect Designer | 20 | Fri | 2008-02-29 10:42 | 28 | Thur | 2008-03-27 10:42 | 89 | Client and Architect
Approve Architect's Design, Ready for DCLU Submission | 5 | Fri | 2008-03-28 10:42 | 7 | Thur | 2008-04-03 10:42 | 90 | Client and Architect
Submit Design to DCLU for Building Permit | 3 | Fri | 2008-04-04 10:42 | 5 | Tues | 2008-04-08 10:42 | 91 | Client and Architect
From the Approved Design, Takeoff the Equipment List | 1 | Wed | 2008-04-09 10:42 | 1 | Wed | 2008-04-09 10:42 | 92 | Client
Make at Decisions on Buying New, Used, or Leased Equipment: | 3 | Thur | 2008-04-10 10:42 | 3 | Mon | 2008-04-14 10:42 | 93 | Takeoff From the Approved Architectural Plans
Keep Leaser Informed of Decisions Affecting the Lease | 1 | Tues | 2008-04-15 10:42 | 1 | Tues | 2008-04-15 10:42 | 94 | Client & Leaser
Update Your Startup Expense & Capitalization Spreadsheet | 1 | Wed | 2008-04-16 10:42 | 1 | Wed | 2008-04-16 10:42 | 95 | Make Any Budget Adjustments
END PHASE 5, LEASE, DESIGN & EQUIPMENT | 55 | Thur | 2008-01-31 10:42 |  | Wed | 2008-04-16 10:42 |  | YOUR DESIGN SHOULD BE COMPLETE AND READY FOR BUILD-OUT
PHASE 6, CONSTRUCTION, INSPECTIONS & APPROVALS | Duration | Start Date |  |  | Finish Date |  | Predecessor | Resource Name
Solicit at Least 3 Suitable Contractors for Bids | 4 | Thur | 2008-04-17 10:42 | 6 | Tues | 2008-04-22 10:42 | 97 | Client
Receive Bids from Contractors and Commence Bid Evaluations | 5 | Wed | 2008-04-23 10:42 | 7 | Tues | 2008-04-29 10:42 | 100 | Client
Check Bidders References, Subcontractors, & Suppliers | 5 | Wed | 2008-04-30 10:42 | 7 | Tues | 2008-05-06 10:42 | 101 | Client
SCORE Contractor Specialist Can Assist | 1 | Wed | 2008-05-07 10:42 | 1 | Wed | 2008-05-07 10:42 | 102 | Client & Score Contractor Specialist
Make Contract Award for Build Out | 7 | Thur | 2008-05-08 10:42 | 9 | Fri | 2008-05-16 10:42 | 103 | Contractor
Construction Build Out By the Contractor | 28 | Mon | 2008-05-19 10:42 | 38 | Wed | 2008-06-25 10:42 | 104 | Contractor
Photo Document the Build Out for Lease Compliance | 28 | Mon | 2008-05-19 10:42 | 38 | Wed | 2008-06-25 10:42 | 104 | Client
Inspections & Approvals by DCLU | 6 | Thur | 2008-06-26 10:42 | 8 | Thur | 2008-07-03 10:42 | 105 | DCLU and Others
Purchase or Lease your Equipment | 1 | Fri | 2008-07-04 10:42 | 1 | Fri | 2008-07-04 10:42 | 107 | For New Equipment,Check the Equipment Warranty Carefully
Schedule Fire Department Inspection for Fire Safety | 1 | Mon | 2008-07-07 10:42 | 1 | Mon | 2008-07-07 10:42 | 108 | Prerequisite to Obtaining Fire Insurance
Purchase Business Liability, Fire, Theft, & Health Insurance | 1 | Tues | 2008-07-08 10:42 | 1 | Tues | 2008-07-08 10:42 | 109 | Client & Insurance Agent
Update Your Startup Expense & Capitalization Spreadsheet | 1 | Wed | 2008-07-09 10:42 | 1 | Wed | 2008-07-09 10:42 | 110 | Client
END PHASE 6, CONSTRUCTION, INSPECTIONS & APPROVALS | 60 | Thur | 2008-04-17 10:42 |  | Wed | 2008-07-09 10:42 |  | Construction is Completed & Permit Approvals Signed
PHASE 7, OPENING THE BUSINESS | Duration | Start Date |  |  | Finish Date |  | Predecessor | Resource Name
Update Your Startup Estimates and Schedule | 2 | Thur | 2008-07-10 10:42 | 2 | Fri | 2008-07-11 10:42 | 112 | Client
If Your Product is New, Consider Test Marketing at a Local Market | 50 | Thur | 2008-07-10 10:42 | 70 | Wed | 2008-09-17 10:42 | 112 | Client
Investigate Barter for Goods & Services | 10 | Thur | 2008-07-10 10:42 | 14 | Wed | 2008-07-23 10:42 | 112 | Client
Sign Wholesale Contract and have Firm Order Policies with Vendors | 10 | Mon | 2008-07-14 10:42 | 14 | Fri | 2008-07-25 10:42 | 115 | Client and Vendors
Establish Order Lead Times, Delivery and Payment Schedules | 10 | Mon | 2008-07-14 10:42 | 14 | Fri | 2008-07-25 10:42 | 115 | Client and Vendors
Negotiate and Start a Business Credit Card Account | 10 | Mon | 2008-07-14 10:42 | 14 | Fri | 2008-07-25 10:42 | 115 | Bank
Purchase Computer Hardware & Software for the Business | 10 | Mon | 2008-07-14 10:42 | 14 | Fri | 2008-07-25 10:42 | 115 | Client and Computer Vendor
Learn the Business Sales Software | 10 | Mon | 2008-07-14 10:42 | 14 | Fri | 2008-07-25 10:42 | 115 | Client and Software Vendor
Purchase Quick Books or Equivalent and Learn the Software | 10 | Mon | 2008-07-14 10:42 | 14 | Fri | 2008-07-25 10:42 | 115 | Client and Software Vendor
Develop Business Logo & Signage | 6 | Mon | 2008-07-14 10:42 | 8 | Mon | 2008-07-21 10:42 | 115 | Client
Attend SCORE Technology/ Internet Workshop | 45 | Thur | 2008-07-10 10:42 | 63 | Wed | 2008-09-10 10:42 | 112 | See SCORE Workshop Schedule for Next Workshop Date
Develop Business Website | 12 | Tues | 2008-07-22 10:42 | 16 | Wed | 2008-08-06 10:42 | 124 | Client and Website Developer
Recommend Attending the SCORE Marketing & Sales Workshop | 50 | Thur | 2008-07-10 10:42 | 70 | Wed | 2008-09-17 10:42 | 112 | SCORE Workshop
Update Marketing Plan Focusing on After Opening Sales Strategies | 2 | Thur | 2008-08-07 10:42 | 2 | Fri | 2008-08-08 10:42 | 126 | Client
Develop Promotional Material | 3 | Mon | 2008-08-11 10:42 | 3 | Wed | 2008-08-13 10:42 | 128 | Client
Develop Your Mailing List | 2 | Thur | 2008-08-14 10:42 | 2 | Fri | 2008-08-15 10:42 | 129 | Client
SCORE Marketing Specialist Review of Your Updated Marketing Plan | 1 | Mon | 2008-08-18 10:42 | 1 | Mon | 2008-08-18 10:42 | 130 | Optional with SCORE Marketing Counselor
Order Printing | 2 | Tues | 2008-08-19 10:42 | 2 | Wed | 2008-08-20 10:42 | 131 | Client
Make All Other Purchases Necessary for opening the Business | 2 | Thur | 2008-08-21 10:42 | 2 | Fri | 2008-08-22 10:42 | 132 | Client and Vendors
Sign Inventory Stocking Contracts | 2 | Mon | 2008-08-25 10:42 | 2 | Tues | 2008-08-26 10:42 | 133 | Client and Vendors
Hire and Train Employees (if required) | 10 | Wed | 2008-08-27 10:42 | 14 | Tues | 2008-09-09 10:42 | 134 | Client
Make Decision for Handling Employee Payroll | 2 | Wed | 2008-09-10 10:42 | 2 | Thur | 2008-09-11 10:42 | 135 | Client or Payroll Service
Write and Distribute Press Release | 2 | Fri | 2008-09-12 10:42 | 2 | Mon | 2008-09-15 10:42 | 136 | Client & Trade Association
Pre-Opening Open House | 1 | Tues | 2008-09-16 10:42 | 1 | Tues | 2008-09-16 10:42 | 137 | Client Invited Guests
Business Grand Opening | 1 | Wed | 2008-09-17 10:42 | 1 | Wed | 2008-09-17 10:42 | 138 | Congratulation to the Client & Their Team
END OF PHASE 7. OPENING THE BUSINESS | 50 | Thur | 2008-07-10 10:42 |  | Wed | 2008-09-17 10:42 |  | Sales and Marketing Now Determine Your Success
AFTER OPENING THE BUSINESS | 1 | Thur | 2008-09-18 10:42 | 1 | Thur | 2008-09-18 10:42 | 140 | Client and SCORE Counselor
ESTIMATED TOTAL TIME FOR DOING A NEW BUINESS STARTUP | 278 | Sun | 2007-08-26 10:42 | 390 | Wed | 2008-09-17 10:42 |  | Includes Design and Construction Time
Copyright 2005 by Seattle Chapter #55, Service Corps of Retired Executives (SCORE)
All rights reserved.